## Activity report_staff1
| Project title |  |  | Special Needs by Placebo: Programme to Advise, Normalize And Control its European Administration. PANACEA
| Agreement number |  |  | 2022-1-IT02-KA220-HED-000088065
| Project beneficiary |  |  | University of Bologna
| Period covered by the Financial Report |  |  | 01/12/2022 to 30/09/2023
| Pnn |  |  | Alma Mater Studiorum - University of Bologna
Activity completion report
Project Partner Institution: |  | University of Bologna
Name and Surname of Employee: |  | XXX YYYY
Type of Employment contract/Formal Link: |  | Post-doctoral researcher
Function in the project: |  | Researcher, teacher and/or trainer |  |  |  | Manager
Activity period: |  | 01/12/2022 to 30/09/2023 |  |  |  | Researcher, teacher and/or trainer
Technical
Amount of time spent on the project by the Employee: | [5 empty] | Administrative
DATE |  |  | Work Package number | Tasks number, Activity's number and details, Output:Deliverables number
Year | Month | Number of days
2023 | January | 5 | WP1 - (learning materials and guidelines) | WP1, Activity 1.1, Planning and organization (KoM in Madrid), Leader UCM Output: KoM summary and Evaluation
2023 | January | 7 | WP1 - (learning materials and guidelines) | WP1, Activity 1.2, Evidence-based content collection: literature review, Leader UNIBO Output: Ongoing
2023 | January | 2 | WP3 - WebApp | WP3, Activity 3.1, Analysis and requirement definition, Leader RE2N Output: Ongoing
2023 | January | 2 | WP4 - Dissemination | WP4, Activity 4.4, Online dissemination Leader JU Output: news about the project and the KoM on Faculty of Medicine UCM website (19/01/2023)
2023 | February | 10 | WP1 - (learning materials and guidelines) | WP1, Activity 1.2, Evidence-based content collection: literature review, Leader UNIBO Output: Ongoing
2023 | February | 2 | WP1 - (learning materials and guidelines) | WP1, Activity 1.3, Practice -based content collection: symposium, Leader EFIC Output: Ongoing
2023 | February | 1 | WP3 - WebApp | WP3, Activity 3.1, Analysis and requirement definition, Leader RE2N Output: Definition of data model
2023 | February | 2 | WP4 - Dissemination | WP4, Activity 4.4, Online dissemination Leader JU Output: UNIBO for Una Europa website (02/02/2023), EFIC twitter account (02/02/2023), EFIC website (03/02/2023), UNIBO Department website (08/02/2023)
2023 | March | 10 | WP1 - (learning materials and guidelines) | WP1, Activity 1.2, Evidence-based content collection: literature review, Leader UNIBO Output: Ongoing
2023 | March | 2 | WP1 - (learning materials and guidelines) | WP1, Activity 1.3, Practice -based content collection: symposium, Leader EFIC Output: Ongoing
2023 | March | 5 | WP3 - WebApp | WP3, Activity 3.2, Planning and organization (in-presence meeting in Leuven), Leader KU Output: Meeting summary and Evaluation
2023 | April | 12 | WP1 - (learning materials and guidelines) | WP1, Activity 1.2, Evidence-based content collection: literature review, Leader UNIBO Output: Ongoing
2023 | April | 2 | WP1 - (learning materials and guidelines) | WP1, Activity 1.3, Practice -based content collection: symposium, Leader EFIC Output: Ongoing
2023 | April | 1 | WP4 - Dissemination | WP4, Activity 4.4, Online dissemination Leader JU Output: news about the project on UCM website (19/04/2023)
2023 | May | 12 | WP1 - (learning materials and guidelines) | WP1, Activity 1.2, Evidence-based content collection: literature review, Leader UNIBO Output: Ongoing
2023 | May | 1 | WP1 - (learning materials and guidelines) | WP1, Activity 1.3, Practice -based content collection: symposium, Leader EFIC Output: Ongoing
2023 | May | 1 | WP4 - Dissemination | WP4, Activity 4.2, Creation of project branding and social media profiles, Leader UNIBO Output: Ongoing
2023 | May | 1 | WP4 - Dissemination | WP4, Activity 4.3, Creation of project website Leader UNIBO Output: Ongoing
2023 | May | 1 | WP4 - Dissemination | WP4, Activity 4.1, Planning and organization (online meeting), Leader JU Output: Meeting summary and Evaluation
2023 | May | 4 | WP4 - Dissemination | WP4, Activity 4.4, Online dissemination Leader JU Output: PANACEA at SIPS congress: JU posted a Twitter about it (12/05/2023). The PANACEA poster has been awarded with the Best Poster Prize (13/05/2023)
2023 | June | 10 | WP1 - (learning materials and guidelines) | WP1, Activity 1.2, Evidence-based content collection: literature review, Leader UNIBO Output: Key publications from a selection of experts on placebo and nocebo have been searched to clarify placebo and nocebo key concepts and definitions. 97 articles have been selected and key definition were extracted. A scoping review of systematic reviews and meta-analyses to examine basic and clinical evidence on placebo and nocebo have been performed. 452 articles have been selected
2023 | June | 1 | WP4 - Dissemination | WP4, Activity 4.2, Creation of project branding and social media profiles), Leader UNIBO Output: PANACEA visual identity, PANACEA social media profiles (Instagram, Twitter, Linkedin)
2023 | June | 2 | WP1 - (learning materials and guidelines) | WP1, Activity 1.3, Practice -based content collection: symposium, Leader EFIC Output: Ongoing
2023 | June | 2 | WP4 - Dissemination | WP4, Activity 4.4, Online dissemination Leader JU Output: Posts on PANACEA social medias
2023 | June | 1 | WP4 - Dissemination | WP4, Activity 4.3, Creation of project website Leader UNIBO Output: Ongoing
2023 | July | 1 | WP4 - Dissemination | WP4, Activity 4.3, Creation of project website Leader UNIBO Output: PANACEA website: https://site.unibo.it/educationonplacebo/en
2023 | July | 15 | WP1 - (learning materials and guidelines) | WP1, Activity 1.4, PLM and PGPN content definition: reading, analysing and summarizing, Leader KU Output: Ongoing
2023 | July | 2 | WP4 - Dissemination | WP4, Activity 4.4, Online dissemination Leader JU Output: Posts on PANACEA social medias
2023 | July | 2 | WP1 - (learning materials and guidelines) | WP1, Activity 1.3, Practice -based content collection: symposium, Leader EFIC Output: Ongoing
2023 | August | 7 | WP1 - (learning materials and guidelines) | WP1, Activity 1.4, PLM and PGPN content definition: reading, analysing and summarizing, Leader KU Output: Ongoing
2023 | August | 1 | WP1 - (learning materials and guidelines) | WP1, Activity 1.3, Practice -based content collection: symposium, Leader EFIC Output: Ongoing
2023 | August | 2 | WP4 - Dissemination | WP4, Activity 4.4, Online dissemination Leader JU Output: Posts on PANACEA social medias
2023 | September | 2 | WP1 - (learning materials and guidelines) | WP1, Activity 1.3, Practice -based content collection: symposium, Leader EFIC Output: Ongoing
2023 | September | 4 | WP1 - (learning materials and guidelines) | WP1, Activity 1.4, PLM and PGPN content definition: reading, analysing and summarizing, Leader KU Output: Ongoing
2023 | September | 2 | WP4 - Dissemination | WP4, Activity 4.4, Online dissemination Leader JU Output: Posts on PANACEA social medias
Total days spent for the Project by the Employee = |  |  |  |  | 137
| Name and surname |  |  | Signature | Date
Staff
PI of the project
Employer Representative and function
Note on E3: Administrator: Name of the partner
Note on A11: Administrator: Insert category Academic/teaching/researcher Manager/Administrative/Technician
Note on B17: Administrator: The activities declared in TS reports must fit the schedule approved by the CE (start - end date of the activities estimated in the proposal).
Note on E17: Administrator: Activity 1.1 runs from 1/12/2022 to 30/01/2023
Note on B63: Administrator: Administrator: insert (Administrative for Human Resources or other representative )

## Activity report_staff2
| Project title |  |  | IN-EULALIA Innovative and Inclusive Instruments for European Latin Linguistic Assessment
| Agreement number |  |  | 2024-1-IT02-KA220-HED-000255464
Activity completion report
Project Partner Institution: |  | University of Roeun
Name and Surname of Employee: |  | Melanie Lucciano
Type of Employment contract/Formal Link: |  | Associate Professor
Activity period: |  | 04/11/2024 -04/03/2025 |  |  |  | Researcher, teacher and/or trainer
Technical
Amount of time spent on the project by the Employee: | [5 empty] | Administrative
DATE |  |  | Work Package number | Tasks number, Activity's number and details, Output:Deliverables number
Year | Month | Number of days
2024 | November |  | WP1 - management | Participation in the kick off meeting in Bologna (18-19/11/2024)
2024 | November |  | WP1 - management | Financial and project management
2024 | December |  | WP1 - management | Financial and project management
2024 | December |  | Wp2 | WP2 Activity 2.1, PREPARATION for cooperative learning
2025 | January |  | WP1 - management | Financial and project management
2025 | January |  | Wp2 | WP2 Activity 2.1, PREPARATION for cooperative learning
2025 | February |  | WP1 - management | Financial and project management
2025 | February |  | Wp2 | WP2 Activity 2.1, PREPARATION for cooperative learning
2025 | February |  | Wp2 | WP2 Activity 2.2 COOPERATIVE LEARNING EXPERIENCE
Total days spent for the Project by the Employee = |  |  |  |  | 0
| Name and surname |  |  | Signature | Date
Staff | Melanie Lucciano