## Slide 1: IN-EULALIA kick off meeting 19/11/2024 Bologna Financial and administrative issues
Francesca Magrefi, Stefania Pollastri
Dipartimento di Filologia Classica e Italianistica

## Slide 2
FINANCIAL MANAGEMENT
IN-EULALIA
Innovative and Inclusive Instruments for European Latin Linguistic Assessment
ERASMUS+ KA220
COOPERATION PARTNERSHIP IN THE FIELD OF HIGHER EDUCATION

## Slide 3
PROJECT
SUBMITTED
MARCH 2024
EVALUATION LETTER RECEIVED
SUMMER 2024
GRANT AGREEMENT SIGNED
30 OCTOBER 2024
PROJECT START 04/11/2024
WHERE ARE WE?

## Slide 4
PROJECT PARTNERS
MANDATE
LETTERS
GRANT AGREEMENT
NATIONAL AGENCY
UNIBO
PROJECT COORDINATOR
EUROPEAN
UNION
IN-EULALIA

## Slide 5
Grant Agreement (G.A)
n. 2024-1-IT02-KA220-HED-000255464
The Grant Agreement (G.A.) has been signed by the National Agency and the project coordinator UNIBO, acting on behalf of all partners (thanks to the mandate letters / accession forms signed at the time of the submission).
The agreement is written in italian.
The main body of the G.A. establishes the main rules and conditions applying to the project (such as duties and rights, total grant, start /end dates, payments, reporting, etc.) ecc.
ANNEXES
The project (partners, activities, budget – AS SUBMITTED TO THE CALL)
Special conditions (financial management)
Mandate letters from partners to coordinator

## Slide 6
Grant Agreement
MAIN FACTS ABOUT THE PROJECT
Project n. | 2024-1-IT02-KA220-HED-000255464
Duration | 36 months
Start – End date | 04/11/24 – 03/11/27
MAX GRANT AMOUNT | 400.000 €
Action to be implemented | Same as in the submitted project proposal
Project Partners | Same as in the submitted project proposal
Financial rules | Lump sum
Other rules | Visibility, IPR, privacy

## Slide 7
OVERALL IN-EULALIA BUDGET
CATEGORY | AMOUNT
WP1 Management | 80.000 EUR
WP2 Building a multilingual and visual Latin lexicon | 78.460 EUR
WP3 Innovative tools for developing intermediate-level lexical skills | 88.360 EUR
WP4 Teaching Latin in a multilingual perspective | 77.300 EUR
WP5 Promoting IN-EULALIA | 75.880 EUR
Total GRANT | 400.00 EUR

## Slide 8
PAYMENTS FROM N.A. TO UNIBO
WHAT | HOW MUCH | WHEN
1° pre-financing payment: 40% of the max grant amount | 160.000 | 30 days after the signature of the grant agreement
2° pre-financing payment: 40% of the max grant | 160.000 | After submission and approval of the Periodic Report ONLY if at least 70% of the amount of first pre-financing payment has been used (July 2026)
Final Report and request for Balance payment: balance (hopefully the remaining 20%) | 80.000 | 60 days after submission and evaluation of the final report, based on the evaluation score obtained by the project (more details in the next phase)

## Slide 9
CONSORTIUM AND PARTNERSHIP AGREEMENTS
GRANT AGREEMENT NATIONAL AGENCY
UNIBO
Unibo
Usal
Unibo
GOTT
Unibo
ROUEN
Unibo
ULISB
Unibo
UCATT
IN-EULALIA: bilateral agreements

## Slide 10
Partnership Agreements between UNIBO and each partner
The Partnership Agreement (PA) regulates: duties of the coordinator and the partners, payments, reporting periods and tasks, management of conflicts, IPR issues, ecc.
ANNEXES:
Grant Agreement (in Italian)
Application form (the submitted project)
Timetable (GANTT)
Partners’ budget

## Slide 11
PAYMENTS FROM UNIBO TO THE PARTNERS
WHAT | HOW MUCH | WHEN
1° pre-financing payment: | 40% of the partner’s budget | After the signature of the partnership agreement
2° pre-financing payment: | 40% of the partner’s budget | After submission and approval of the Periodic Report ONLY if at least 70% of the amount of first pre-financing payment has been used
Balance payment: | The remaining 20% | 60 days after submission and evaluation of the final report, based on the evaluation score obtained by the project

## Slide 12
OFFICIAL REPORTING TO THE NATIONAL AGENCY
 | Period covered | DEADLINE FOR PARTNERS’ CONTRIBUTION (P.A.)
PROGRESS REPORT | 04/11/24 - 01/10/25 | 01/10/2025
PERIODIC REPORT (and request of the 2° Payment) | 04/11/24 - 30/03/26 | 30/03/2026
FINAL REPORT (and request of final payment) | 04/11/24- 03/11/27 | 03/11/2027
Final deadline for submission to the N.A. as established by the G.A.
01/11/2025
30/04/2026
02/01/2028

## Slide 13
IMPLEMENTATION OF THE PROJECT
Beneficiaries must implement the action as described in the approved project proposal (annex to the G.A. and P.A.)
ANY CHANGES TO THE PROJECT ACTIVITIES, RESULTS, OBJECTIVES, BUDGET - IF THEY OCCUR - NEED TO BE AUTHORISED BY THE NATIONAL AGENCY AND LEAD TO AN AMENDMENT OF THE AGREEMENT, e.g.
Duration of the project
Legal status of the partner organisations
Consortium composition
Budget assigned to the workpackages
Relevant changes to the workpackages and activities
The Coordinator is responsible for managing the project, submitting reports, acting as intermediary for all contacts with the EU Granting Authority (including amendments, if any).
All partners shall promptly inform the Coordinator of any delay /change in which they might incur in performing the project activities.

## Slide 14
IMPLEMENTATION OF THE PROJECT
In what concerns the planned activities, changes are possible on condition that the changed activities are content equivalent, meaning that the new/modified activity contributes to the project objectives, and budget equivalent, meaning that the modified activity has an approximately equivalent cost as the planned one.
However, as the cases can be very different from each other it is recommended to always consult the N.A. (through the coordinator)
All changes in the project must be duly explained and justified in the reporting to the N.A.

## Slide 15
OVERALL IN-EULALIA BUDGET per WP / PARTNER
 | WP1 | WP2 | WP3 | WP4 | WP5 | Total
Università di Bologna | 21.500,00 € | 17.580,00 € | 16.780,00 € | 10.820,00 € | 16.280,00 € | 82.960,00 €
Università di Salamanca | 12.000,00 € | 11.640,00 € | 10.160,00 € | 8.660,00 € | 15.360,00 € | 57.820,00 €
Università di Rouen | 12.000,00 € | 14.500,00 € | 15.280,00 € | 10.600,00 € | 15.140,00 € | 67.520,00 €
Università di Göttingen | 12.000,00 € | 14.280,00 € | 20.560,00 € | 9.200,00 € | 13.960,00 € | 70.000,00 €
Università di Lisbona | 12.000,00 € | 12.060,00 € | 13.360,00 € | 7.450,00 € | 9.320,00 € | 54.190,00 €
Università Cattolica del Sacro Cuore | 10.500,00 € | 8.400,00 € | 12.220,00 € | 30.570,00 € | 5.820,00 € | 67.510,00 €
Total | 80.000,00 € | 78.460,00 € | 88.360,00 € | 77.300,00 € | 75.880,00 € | 400.000,00€

## Slide 16: IN-EULALIA BUDGET
WP1 budget
The project management work package represents maximum 20% of the total budget of the project and does not require the indication of specific objectives, as it is considered to contribute horizontally to all the objectives of the project.
It includes costs for participation to / organization of the KoM in Bologna (2 days, 2 persons per partner).
Activities covered:
  Project management of the local unit
  Financial management
  Evaluation activities
  Organisation of meetings
  Reporting
  etc
 | WP1
Università di Bologna | 21.500,00 €
Università di Salamanca | 12.000,00 €
Università di Rouen | 12.000,00 €
Università di Göttingen | 12.000,00 €
Università di Lisbona | 12.000,00 €
Università Cattolica del Sacro Cuore | 10.500,00 €

## Slide 17: IN-EULALIA BUDGET
The budget of each WP is the sum of the cost of each activity included in this WP (except for WP1 project management and kick-off meeting)
The budget of each ACTIVITY includes the following costs categories:
  Staff: calculated on the basis of the n. of working days and the unit cost defined for each partner country for Researcher/Teacher/Trainer (the only staff category used in the project) having a formal link with the partner institution
  The n. of days assigned to each partner vary proportionally to the complexity of the tasks and is higher for the coordinator of the activity.
  Travels: calculated on the basis of the n. of persons travelling and the unit cost for the distance covered.
  Other costs covering organizational costs for catering, invited speakers, promotional materials, etc.
  Subsistence (for summer the school -LTT): defined on the basis of the unit costs per day of staying, the n. of days and the n. of participants. Only in WP4 Teaching Latin in a multilingual perspective
IMPORTANT:
Staff involved in the project must have a formal link with partner institution (e.g. ongoing contract, permanent or temporary, fellowship, etc.).

## Slide 18: The Budget file
Let’s have a closer look to the budget file

## Slide 19: CONTINOUS MONITORING: REPORTING TOOL
In order to be able to perform a continuous monitoring of the project, we will periodically collect from each person involved in the project an
ACTIVITY REPORT (+ formal link declaration)
The N.A. can perform on the spot checks and visits during and after the project duration. N.A. will verify different aspects such as organisational structure of the partnership, activities and results against the application form, staff involved, cost documentation and financial management, monitoring tools and actions, etc.
1 report per person
Every 6 months
1° report May 2025 (before meeting in Lisbon)

## Slide 20: IN-EULALIA BUDGET
FORMAL LINK?
We will collect a formal link declaration for each person involved in the project (explaining role and employment contract).
Example:
This is to certify that the Prof. LUCIA PASETTI, permanent employee of the University of Bologna, with reference to the period from 04/11/24 –01/11/25 is full professor at the Department of Classical Philology and Italian Studies – FICLIT.
- signed by the head of administration/department or the legal representative

## Slide 21
UNIBO sends the model of P.A. by 5th December
Partners discuss it with their own administrative / research manager
Partners send their feedbacks by 18th December
UNIBO sends the final version of the P.A. 15th January 2025
Partners complete the P.A. with their data and send it back to UNIBO for final check
The partner’s legal representative signs the agreement and sends it to UNIBO
UNIBO signs the agreement and makes the money transfers (beginning of February)
IMPORTANT: for each partner, we need a contact person for any administrative issues
SIGNATURE OF THE PARTNERSHIP AGREEMENT

## Slide 22
COMMUNICATION, DISSEMINATION AND
VISIBILITY
Art. 17
The beneficiaries shall acknowledge the support received under the Erasmus+ programme in all communication and promotional material, including on websites and social media. The guidelines for the beneficiaries and other third parties are available at Communicating and raising EU visibility - European Commission
Art. 17.3
Any communication or publication that relates to the action, made by the beneficiaries jointly or individually in any form and using any means, must include the following QUALITY OF INFORMATION DISCLAIMER:
(a) that it reflects only the author’s view; and
(b) that the is not responsible for any use that may be made of the information it contains
“Funded by the European Union. Views and opinions expressed are however those of the author(s) only and do not necessarily reflect those of the European Union or Italian National Agency for Erasmus+. Neither the European Union nor the granting authority can be held responsible for them.”

## Slide 23: Credits:
Francesca Magrefi – Stefania Pollastri
Dipartimento di Filologia Classica e Italianistica
francesca.magrefi@unibo.it
stefania.pollastri3@unibo.it